## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Color
PROJECT: DnDBeyondUnderGround
|  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned | [5 empty] | Revieuw moment
Project start date: | 2024-02-19 |  |  |  | February | [13 empty] | March | [27 empty] | April
Scrolling increment: | 1 | time axis 2024-02-20 to 2024-04-15
Milestone description | Category | Progress | Start | Days | time axis 2024-02-20 to 2024-04-15
2024-03-13
Initiation & Planning |  |  | 2024-02-19
Define Goals | Low Risk | 100% | 2024-02-19 | 5
Make Agenda | Low Risk | 100% | 2024-02-19 | 5
Design Data Model | Low Risk | 100% | 2024-02-19 | 5
Develop Wireframes | Low Risk | 100% | 2024-02-19 | 5
Make Requirements List | Low Risk | 100% | 2024-02-19 | 5
Make Pitch | Low Risk | 100% | 2024-02-19 | 5
Drupal & NextJs Development |  |  | 2024-02-26
Spell List | Goal | 0% | 2024-02-26 | 5 | 2024-02-26: 2; 2024-02-27: 2; 2024-02-28: 2; 2024-02-29: 2; 2024-03-01: 2
as a user i want to be able to see a spell list | On Track | 100% | 2024-02-27 | 2
as a user i want to be able to see a detailed spell | On Track | 100% | 2024-02-29 | 2
drupal | On Track | 100% | 2024-02-26 | 1
nextjs | On Track | 95% | 2024-02-27 | 4
Monster List | Goal | 0% | 2024-03-04 | 4 | 2024-03-04: 2; 2024-03-05: 2; 2024-03-06: 2; 2024-03-07: 2
as a user i want to be able to see a monster list | On Track | 80% | 2024-03-05 | 2
as a user i want to see a detailed monster | On Track | 100% | 2024-03-06 | 2
drupal | On Track | 100% | 2024-03-04 | 1
nextjs | On Track | 90% | 2024-03-05 | 3
Class List | Goal | 0% | 2024-03-11 | 4 | 2024-03-11: 2; 2024-03-12: 2; 2024-03-13: 2; 2024-03-14: 2
as a user i want to see a class list | On Track | 20% | 2024-03-12 | 2
as a user i want to see a detailed class | On Track | 80% | 2024-03-13 | 2
drupal | On Track | 80% | 2024-03-11 | 1
nextjs | On Track | 60% | 2024-03-12 | 3
Artefacts List | Goal | 0% | 2024-03-18 | 4 | 2024-03-18: 2; 2024-03-19: 2; 2024-03-20: 2; 2024-03-21: 2
as a user i want to see an artefacts list | On Track | 0% | 2024-03-19 | 2
as a user i want to see a detailed artefact | On Track | 0% | 2024-03-20 | 2
drupal | On Track | 0% | 2024-03-18 | 1
nextjs | On Track | 0% | 2024-03-19 | 3
Race List | Goal | 0% | 2024-03-25 | 4 | 2024-03-25: 2; 2024-03-26: 2; 2024-03-27: 2; 2024-03-28: 2
as a user i want to see a race list | On Track | 0% | 2024-03-26 | 2
as a user i want to see a detailed race page | On Track | 0% | 2024-03-27 | 2
drupal | On Track | 0% | 2024-03-25 | 1
nextjs | On Track | 0% | 2024-03-26 | 3
Feats List | Goal | 0% | 2024-04-01 | 3 | 2024-04-01: 2; 2024-04-02: 2; 2024-04-03: 2
as a user i want to see a list of feats | On Track | 0% | 2024-04-02 | 2
drupal | On Track | 0% | 2024-04-01 | 1
nextjs | On Track | 0% | 2024-04-02 | 2
Conditions List | Goal | 0% | 2024-04-08 | 3 | 2024-04-08: 2; 2024-04-09: 2; 2024-04-10: 2
as a user i want to see a list of conditions | On Track | 0% | 2024-04-09 | 2
drupal | On Track | 0% | 2024-04-08 | 1
nextjs | On Track | 0% | 2024-04-09 | 2
API fetching | Goal | 0% | 2024-04-08 | 0
research & test api | On Track | 0% | 2024-02-26 | 0.72727
write data translation | On Track | 0% | 2024-02-26 | 0.72727
drupal implementation | On Track | 0% | 2024-04-08 | 0.72727
Search Api | Goal | 0% | 2024-02-26 | 0
Research & Testing | On Track | 0% | 2024-02-26 | 0.72727
Implement data | On Track | 0% | 2024-02-26 | 0.72727
drupal | On Track | 0% | 2024-02-26 | 0.72727
nextjs implementation | On Track | 0% | 2024-02-26 | 0.72727
Character | Goal | 0% | 2024-02-26 | 0
as a user i want to create a character |  | 0% | 2024-02-26 | 1
as a user i want to see the created character sheet |  | 0% | 2024-02-26 | 1
as a user i want to export the character sheet into a pdf |  | 0% | 2024-02-26 | 1
as a user i want to have an interactive character sheet |  | 0% | 2024-02-26 | 1
research character creation logic |  | 0% | 2024-02-26 | 1
implement character creation logic |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
TITLE |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
TITLE |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
TITLE |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
TITLE |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
TITLE |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
goal |  | 0% | 2024-02-26 | 1
drupal |  | 0% | 2024-02-26 | 1
nextjs |  | 0% | 2024-02-26 | 1
Research |  |  | 2024-03-13
Task 1 |  | 0% | 2024-03-13 | 4
Task 2 |  | 0% | 2024-03-13 | 14
Task 3 |  | 0% | 2024-03-13 | 6
Task 4 |  | 0% | 2024-03-13 | 3
Task 5 |  | 0% | 2024-03-13 | 19
TITLE 4 |  |  | 2024-03-13
Task 1 |  | 0% | 2024-03-13 | 15
Task 2 |  | 0% | 2024-03-13 | 5
Task 3 |  | 0% | 2024-03-13 | 1
Task 4 |  | 0% | 2024-03-13
Task 5 |  | 0% | 2024-03-13
2024-03-13
To add more data, Insert new rows ABOVE this one |  |  | 2024-03-13

## Data Modelling
Spell
title
level
schools[taxonomy]
casting time
range
components[taxonomy]
description
classes[relation]
Class
Title
description
HitDie
Proficiencies[taxonomy]
Features[relation]
Spells[relation]
Passives[relation]
Race
Name
Description
Traits[relation]
Subraces[relation]
Artefact
Name
Type[relation]
Description
Properties
Weight
Value
Feat
Condition
Monster
Character